## Bug Report
Defect No. | Status | Raised By | Tested on Version | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity | Screenshot | Bug Description | Test Data
BR_01 | Open | Adham Koteishi | Version 1.0 | P03 | 1- Go to "Products" page. 2- Observe the product grid layout and check that all products are properly aligned in rows and columns. 3- Scroll through the page to identify any missing spaces or blank slots where a product should appear. 4- Press TAB and move to next field. | All product tiles should be aligned properly in rows and columns with no missing or blank slots while tabbing through the page. | Blank spaces appeared where product images should be in rows 4, 7, 11, and 12; tab navigation skips empty slots | High | High | #VALUE! | Blank spaces appear in product grid. | N/A
BR_02 | Open | Adham Koteishi | Version 1.0 | P17 | 1- Go to "Products" page. 2- Locate the "Category" section on the left side. 3- Click on "Kids" to expand the category options. 4- Click on "Dress" under the Kids section. 5- Observe the displayed products to confirm the correct filtering. 6- Press TAB and move to next field | Only Kids’ Dresses should appear in the product list. | Tops and Shirts appeared along with the Dresses. | High | High | #VALUE! | Kids → Dress filter displays incorrect product results | Category: “Kids → Dress
BR_03 | Open | Adham Koteishi | Version 1.0 | P20 | 1- Go to "Products" page. 2- Apply a category filter (e.g., “Women → Dress”). 3- Use the search bar to search for a keyword within that filter (e.g., “Pink”). 4- Observe the product results displayed after search. 5- Press TAB and move to next field | Both filters combine — only pink dresses should appear within the “Women → Dress” category | Search filter does not appear or return any results within subcategories | High | High | #VALUE! | Search and category filters not integrated correctly | Filter: “Women → Dress”, Search: “Pink
BR_04 | Open | Adham Koteishi | Version 1.0 | P26 | 1- Go to "Products" page. 2- In the search bar, enter a multiple-word product name (e.g., “Summer Dress”). 3- Click the search button to perform the query. 4- Observe the displayed results for matching products. 5- Press TAB and move to next field | All products containing both words (“Summer” and “Dress”) should appear in the results | No products appeared after searching a multiple-word query | Medium | Medium | #VALUE! | Multiple-word search query returns no results | Search: “Summer Dress”
BR_05 | Open | Adham Koteishi | Version 1.0 | P32 | 1- Go to "Products" page. 2- Type “dress” in the search bar. 3- Click the Search button. 4- Observe the displayed product results. 5- Press TAB and move to next field | Only products related to dresses should be displayed. | Page loaded with tops and shorts along with the dresses. | High | High | #VALUE! | Search for “Dress” returns unrelated products | Search: “Dress”
BR_06 | Open | Adham Koteishi | Version 1.0 | P33 | 1- Go to Home Page of the website. 2- Check if the Search Bar is visible and functional. 3- Click on “Products” from the navigation bar. 4- Verify that the Search Bar is visible on the Products page. 5- Click on any Category (e.g., “Women → Dress”). 6- Check if the Search Bar is visible on the Category page. 7- Try searching for “dress” and observe results. 8- Press TAB and move to next field. | The search bar should be visible and functional on all pages (Home, Products, Category). Relevant products should appear | Search bar visible and functional on Home and Products pages, but not visible on Category page | High | High | #VALUE! | Search bar missing on Category pages; integration across pages broken | Search: “dress”, “tops”, “jeans”, “kids
BR_07 | Open | Adham Koteishi | Version 1.0 | P45 | 1- Go to "Products" page. 2- Scroll to the Brands section on the left side. 3- Click on the Polo brand. 4- Verify that all displayed products have: - Product image loaded correctly (no broken icons) - Product name visible and relevant to Polo - Product price displayed and formatted properly. 5- Repeat step 3–4 for each remaining brand (H&M, Madame, Mast & Harbour, Babyhug, Allen Solly Junior, Kookie Kids, Biba). 6- Check layout consistency (aligned images, no gaps, proper spacing). 7- Press TAB and move to next field | Each brand page should display only its own products, all with correct images, names, and prices — no missing, broken, or unrelated product images. | Polo: Images loaded but unaligned. H&M: Product images unaligned. Madame: Product images unaligned. Mast & Harbour: Product images unaligned. Babyhug: All products and images displayed correctly and aligned. Allen Solly Junior: Product images unaligned. Kookie Kids: Product images unaligned. Biba: Product images unaligned | High | High | #VALUE! | Product images and layout inconsistent across brands | Brands: Polo, H&M, Madame, Mast & Harbour, Babyhug, Allen Solly Junior, Kookie Kids, Biba
BR_08 | Open | Adham Koteishi | Version 1.0 | P46 | 1- Go to "Products" page. 2- In the Search Product field, type “jeans” and click Search. 3- After results load, scroll to the Brands section. 4- Click on the Polo brand. 5- Observe filtered products. 6- Press TAB and move to next field | Only Polo jeans should appear (search results combined with brand filter). | Search results reset; brand filter overrides search | High | High | #VALUE! | Brand filter overrides search results instead of combining filters | Search: “jeans”, Brand: Polo
BR_09 | Open | Adham Koteishi | Version 1.0 | P47 | 1- Go to "Products" page. 2- Enter “tops” in the search field and click Search. 3- After results load, click Babyhug brand under Brands. 4- Wait for results to load. 5- Click Biba brand next. 6- Observe if search input still shows “tops” and results update. 7- Press TAB and move to next field | Search text should remain in input; only Biba tops should appear | Search term clears and results reset after switching brands; search bar doesn’t appear in any brand. | High | High | #VALUE! | Search bar loses input and fails to persist when switching brands | Search: “tops”, Brands: Babyhug → Biba